## Cover Page
Team #: | 4
Project Name: | Reduce Food Waste in Cafeterias
Team Members: | Sertina Augustine Maliyakal, Christopher Moody, Divyanshu Gupta, Diego Vidaurre Villagomez, Oleksandra Zaiats

## Risk Register
Risk Register
| Name of Project | Reduce Food Waste in Cafeterias
Risk ID | Risk Statement | WBS # (if applicable) | Risk Category | Risk Owner | Probability | Impact | Risk Response
| Use the 'if-then' format At least 2 should be positive risks | Provide the WBS ID that may be/is impacted by the risk | Provide the category of the risk (e.g., Cost Risk, Stakeholder Risk, Scope Risk, etc.) | Name of person who monitors the risk and explain why they are the best person | Use the scale in the next tab and explain why you give that rating | Use the scale in the next tab and explain why you give that rating | Clearly indicate the risk response strategy (e.g. avoid, transfer, etc.) and explain why it is the best strategy
1 | If stakeholders do not agree on project idea on kickoff meeting, then several other meetings will be required to discuss project scope | 1.2.3 | Scope Risk | Project manager monitors the risk, PM is an ideal resource for this risk because he/she has good grip on project scope and associated challenges they may come as we move forward. | Low, as everyone has the same vision going into the project | Moderate, as this would cause a moderate schedule delay (5%-10%) and a Moderate increase in the scope as the scope will have to be change to make everyone agree on a plan | Accept, this risk works towards the successful implementation pf project even though the project schedule is moved by a week.
2 | If the market study we perform comes back with skewed data, then it would throw off the scope for the project | 1.1.1 | Scope Risk | Divyanshu Gupta, Business Analyst. As the business analyst he is in charge of assuring that we are receiving the correct information and that the information is from a creditable source | Low, as there are many studies done already that our Business Analysis can compare against our scope | Moderate, as this would increase the schedule to perform a correct market research report, as well as increasing the cost by a moderate amount (10%-20%). Scope will also slightly change but the main idea of the project scope will stay the same | Avoid, what we would do is make sure that our business analyst is taking information from creditable sources. We would also have another business analyst double check the work
3 | If there is delay in acquiring the training course on Lean Path technology, the operational staff will not be trained on time to handle the technology and any issues. | 3.4.1 | Project Team risk | Project coordinator monitors the risk as this will have an impact on the project team operations and schedule. | Low, as Lean path courses are available online. | Low as scope and cost of the project will only be affected slightly (<5%) and the quality of the project will not be degraded. | Mitigate, research and find the ideal Lean Path training course and supplemental training courses with enough functional knowledge which are available easily that can be used for basic training.
4 | If Lean Path Spark is not available in the next 2 months to provide service then the project could be delayed. | 3.1.1 | Schedule Risk | Christopher Moody, Project Manager. As this could have a direct impact on the project schedule the project manager should be in charge of responding to this risk. | Low. Historical data suggests that Lean Path Spark usually has availability for this kind of projects. | High. Lack of availability of the supplier could have a big impact (over 15%) on the project schedule. | Mitigate, contact the supplier with anticipation so they can schedule their availability. This would be the best strategy as it would be cost effective and help in minimizing the risk.
5 | If the decisions undertaken for the project plan finalization is not accepted mutually by the project team and George Brown Cafeteria Director, there will be conflicts between the stakeholders for varied requirements. | 2.2.3 | Stakeholder Risk | Project Manager as this can impact the scope and timeline of the project. | Moderate, stakeholder conflicts arise frequently as different stakeholders have different requirements and a mutual understanding needs to be reached for a decision. | Moderate, this will affect the scope, time and even the cost of the project | Accept, stakeholder conflicts can be resolved when it occurs through proper communication and sharing of ideas. The conflicts can even work towards successfully achieving the project goals without scope creep.
6 | If our delivery vehicle have a breakdown, then the deliveries to the food banks, and homeless shelters could be delayed which may reduce food shelf life as well | 3.2.3 | Scope Risk | Oleksandra Zaiats, Project Coordinator. This would impact our project coordinator as it is their job to make sure that all deliveries are on time. | Low, car breakdowns are not common and would happen a low amount of the time | Low, This would have a low impact on the schedule as it would only delay us 1 or 2 days, as well it would have a low impact on the cost as we will need to get the delivery vehicle fixed | Mitigate, We will keep our delivery vehicles in working condition, regularly doing checkups to make sure they are running smoothly
7 | If there is supply chain issues with ordering small plates and storage containers, then George brown will be forced to serve and store food is more wasteful containers and plates | 3.3 | Scope Risk | Oleksandra Zaiats, Project Coordinator. This would have an impact on the project coordinator as they are in charge of making sure the kitchen has the plates and storage containers it needs | Low, online there are many of different suppliers would be easy to find a replacement | Low, Lack of proper plates and storage containers will only slow the schedule by a low amount (<5%) and the scope will have a very minor change as we are delaying our scope by a low amount (<5%) | Mitigate, We will have a list of backup suppliers that we will be able to contact if our main supplier has a shortage
8 | If cafeteria team needs additional time (weeks) than scheduled time to gain confidence on using lean path Spark technology then it would be an added advantage as better understanding of system would lead to less reported issues during hyper care support period. | 5.2.3 | Scope Risk | Project manager monitors the risk, PM is an ideal resource for this risk because he/she will be in regular contact with cafeteria team and Lean Path Spark team to note feeback on new system | Moderate, chances that handover operations to cafeteria team can be extended readily depending on how readily cafeteria team gets familiar with using Lean path spark software | Low, It acts as an advantage to the project as more functional and tecnical issues can be solved during training in the handover step of the project helping to reduce fuiture training and maintenance costs | Accept, this risk works towards the successful implementation of project even though the project schedule is moved by a week.
9 | If the planned training is not adequate and is not effective for the cafeteria staff, then the project would face issues during the implementation. | 3.4.3 | Scope Risk | Christopher Moody, Project Manager. As this could have a direct impact the project scope. | Low, there is previous experience on staff training. | Moderate, the impact is manageable as there is just a moderate scope change. | Mitigate, monitor the advancement and the quality of the training. This is the best strategy as it maintains the plan while also monitoring the possible risk.
10 | If ordering & cooking more food materials for cafeterias food leads to more food wastage then homeless shelters/foodbanks/orphanges can benefit from it | 3.2.2 | Cost Risk | Project coordinator monitors the risk as this will have an impact the amount of food wasted. | Moderate, It is hard to exactly pinpoint how many poeple will be eating in the dinning hall each meal | Low, as there will me a small change to cost as ordering more raw materials is more costly | Enhance, we will use this oppurtunity to give more back to the community and make sure that the food is not wasted
Avoid, Transfer, Mitigate, Accept